CLIENT REPORT (CASE 01)

Title: DSS Case Report

Client: IT Step Academy (Poland branch)

Date: February 4, 2026

Case ID: CASE-01-ITSTEP-PL

Decision owner: Branch Director (management decision owner)

0) DECISION STATUS (MANDATORY)

☑ DECISION READY

☐ REQUIRES MANDATORY INPUT CLARIFICATION

☐ DECISION IMPOSSIBLE UNDER CURRENT CONDITIONS (Decision Lock)

1) DECISION LOCK (HARD COMMITMENT)

- ACCEPTED DECISION (single, no alternatives):

Launch a 60‑day operational plan to grow enrollment by improving funnel quality (content → lead → event → contract) with focus on conversion, CRM discipline, and event execution quality, without changing the product portfolio.

- REJECTED ALTERNATIVES (list):

1) “Rely only on expensive direct high‑intent leads with low volume.”

2) “Expand the product line before stabilizing conversion.”

3) “Deep price discounting to chase volume.”

- OWNER CONFIRMATION:

“I, __________________, accept this decision and take responsibility for execution.”

2) SHORT SUMMARY

- Problem in 1–2 sentences:

The branch consistently misses enrollment targets and fails to launch new groups; within 2 months it must restore positive cash flow.

- Why this is urgent now:

Current funnel quality and conversion levels keep the branch in a financial deficit.

- Target result (measurable):

Within 2 months launch 6 adult groups (PL/EN/RU), +60 students, +50–60k PLN/month cash flow; within 1 month launch 3 adult groups (15 each) + 1 kids group.

3) PROBLEM STRUCTURE (MINIMUM)

- System boundary (inside/outside):

Inside: local branch (marketing, sales, events, delivery, HR, local content/execution). Outside: central office (ad targeting and programs). Market/economy/regulation are external conditions but under the director’s managerial responsibility.

- Key actors and interactions:

Branch Director → content maker → targeting (central office) → leads → sales team → events → contracts; instructors and training programs as part of the customer promise.

- Core contradiction:

Cheap leads are low quality and don’t convert; expensive leads are high quality but too few and still not fully converted.

4) IDEAL FINAL RESULT (IFR)

- IFR statement:

Within 2 months the branch launches 6 groups and gains +60 students with stable training quality and no product expansion.

- “No new harm” condition:

Do not reduce training quality, do not dump price, and do not burn out the team.

5) EXECUTION PLAN (2–4 weeks)

- Workstream 1: Positioning and content

Tasks:

- Within 7 days define value messages by program (PL/EN/RU).

- Rebuild creatives and event сценарии around target pains.

- Run events with an external host or retrain the host.

- Workstream 2: Sales funnel and CRM discipline

Tasks:

- Enforce lead response SLA (time to first contact, number of touches).

- Restart qualification scripts and follow‑up scenarios.

- Weekly conversion audit: lead → confirmed → show‑up → contract.

6) METRICS & VERIFICATION

- Leading indicators:

- Valid leads/week (target: +50% vs baseline).

- Event show‑up rate (target: ≥30% of confirmations).

- Event‑to‑contract conversion (target: ≥10%).

- Outcome metrics:

- Groups launched (target: 3 by month 1; 6 by month 2).

- New students (target: +60 in 2 months).

- Cash flow (target: +50–60k PLN/month).

- Success criteria:

Actual group launches and cash flow increase confirmed by the branch director.

7) COST OF ERROR (MANDATORY)

- Cost of non‑decision:

Continued cash flow deficit and risk of branch closure/restructuring.

- Cost of rule violation:

Budget wasted on low‑quality leads and loss of the 2‑month window.

- Cost of alternative path:

Relying only on expensive direct leads yields insufficient volume to launch the required groups.

8) RULE (OPERATIONAL)

If for 2 consecutive weeks event‑to‑contract conversion < 10% and show‑up < 30%, then replace the event host and сценарий, and rebuild creatives with new messages.

Scope/exceptions:

Applies to all branch events regardless of audience language.

Rule owner: client (branch director).

9) GUIDED CORRECTION (IF “REQUIRES INPUT CLARIFICATION”)

Not applicable: input data is sufficient to make a decision.

10) CLIENT SEES ONLY THE INTERPRETATION

- Client status:

☑ “DECISION READY”

☐ “REQUIRES MANDATORY INPUT CLARIFICATION”

☐ “DECISION IMPOSSIBLE UNDER CURRENT CONDITIONS”

Appendix (optional)

- Risks/notes: director skill gaps; risk of weak content quality; dependency on central office for programs.

- Internal artifacts: Intake Q1–Q8, system boundary, contradiction, metrics.